## 35-50 day grid
PRODUCTION SCHEDULE — 35-50 day grid
Twenty milestones from tech pack sign-off to container loading. The window runs from sample approval, not from the order.
# | Milestone | Owner | Window | What gates it | Evidence attached | Weekly check | Actual date
01 | Tech pack signed off and golden sample retained | Buyer | Day 0 | Signed tolerance sheet; one golden sample retained at origin | Photograph of the signed pack and the retained unit
02 | Carrying charge: material release order placed | Planning | Day 1-2 | BOM lines with the longest lead time identified | Purchase order acknowledged
03 | Face fabric ordered and confirmed | Sourcing | Day 2-12 | Booking date from the mill; the longest line sets acceptance | Mill confirmation
04 | Lining, foam and board ordered | Sourcing | Day 2-10 | Consumption from the BOM against the order quantity | Acknowledged order
05 | Hardware and zips ordered | Sourcing | Day 2-14 | Named hardware is the most common source of slip | Supplier confirmation with the finish stated
06 | Lab test booked where required | Quality | Day 3 | Some tests need three weeks of laboratory time | Booking reference
07 | Lab dips and artwork proof issued | Product | Day 3-8 | Two rounds of dips are usual before approval | Dip card or proof sheet
08 | Lab dips approved | Buyer | Day 8-12 | Approval here is the gate for bulk dyeing | Signed-off dip
09 | Counter sample made | Sample room | Day 10-16 | Sampling window is 6-10 working days, 12-15 if complex | Counter sample unit
10 | Counter sample couriered and reviewed | Both | Day 16-22 | Courier time sits outside the factory window | Tracking and review notes
11 | Pre-production meeting held | Planning | Day 20 | Line, method and any jigs agreed before cutting | Signed meeting minute
12 | Bulk materials received and inspected | Quality | Day 20-26 | Fabric inspected before it is cut, not after | Inward inspection record
13 | Cutting begun | Production | Day 26-28 | Marker efficiency here sets the yield | Cutting start record
14 | Printing or embroidery completed | Production | Day 28-32 | Artwork placed against the approved proof | First-off approval sheet
15 | Assembly on line | Production | Day 30-40 | The longest single block in the window | Daily line output sheet
16 | In-line inspection | Quality | Day 32-42 | Corrected while the line can still be changed | In-line record
17 | Final random inspection | Quality | Day 42-46 | AQL 2.5, ISO 2859-1, General Inspection Level II | Inspection report with the sample size stated
18 | Packing and carton marking | Production | Day 44-48 | Carton count and marking checked at pack-out | Packing list
19 | Freight booking and customs entry papers | Shipping | Day 46-50 | Booked against the vessel, not against hope | Booking note
20 | Container loading and departure | Shipping | Day 48-50 | Loading supervision record retained | Loading photograph and seal number
Locked programme numbers ¦ MOQ: 500 pcs per style and colourway (300 negotiable on a repeat) · Sampling: 6-10 working days; 12-15 where the construction is complex · Bulk production: 35-50 days after sample approval · Inspection: AQL 2.5, ISO 2859-1, General Inspection Level II · Payment: T/T 30/70 Terms: FOB Xiamen (CIF/DDP available)
The weekly checkpoint column is the one that matters to a buyer: it is read every seven days and it names the milestone the programme is sitting on. A date that cannot be shown against a milestone is a promise, not a schedule.